## Main
Priority | Status | Type | Name | Desc
Phase 2 | Not Started | Feature | Background | A background node that is (maybe parallax?) behind the map node
Phase 1 | Not Started | Feature | More Parts | A variety of parts (1-3 for each type)
Phase 2 | Not Started | Bug | 2 Parts 1 Connector | When a part is already on a connector, and another one comes along, it mounts
Phase 2 | Not Started | Bug | Killer Connector | When a part goes over a connector when held, it cant connect to anything until re-selected
Phase 2 | Not Finished | Feature | Localization | Needs csv files
Phase 1 | Not Started | Feature | Parts Area | An area, at the bottom center of the screen
Now | Not Started | Feature | Tutorial | The tutorial levels
Phase 1 | Not Started | Feature | More Levels | A bunch of levels (1-3 for each category)
Now | Not Finished | Change | Machine Movement | Machine movement is very finiky (idk how its spelled)
Now | Finished | Feature | Collection | A screen which tells you details of parts, skins you have and etc…
Now | Not Finished | Feature | End Level Menu | A small menu that pops up when the player wins/loses

## Data
Type | Status | Priority
Bug | Not Started | Now
Change | Not Finished | Phase 1
Feature | Finished | Phase 2